| Project Plan Choosing the Chance to Change- Reducing Obesity in people with learning disabilities (September 07– September 09) 10th July 2008 |
| --- |
| Project objectives | Item | Progress and Actions | Lead | Date |
| Partnership working | Establish Obesity working Group | Working Group established, linked to Obesity Strategy and Health Promotion Group Link to wider Equality Agenda | Stephan Brusch and Marian Marsham Brian Colman | 27.10. 07 |
|  | Link to the Olympics/ Para-Olympics 2012 | Stephan to meet with disability lead in London Sports Forum Link with CSPAN (Richard Barker)- Invite new Disability Spots lead in Westminster City Council. Invited new Disability lead to the group | Alan Whetherley Stephan Brusch and Jonathan Hearn | Ongoing |
|  | Implement Obesity Communication strategy | Letter sent to all stakeholders and included in PCP bulletin. Emailed all Health Facilitators | Marian Marsham and Stephan Brusch | 11.01.08 |
|  |  | WLDP’s website to include information on physical activities and other health information Make links to the Wire Well being site | Derry Pitcaithly, Liz Atkinsen and Claudia Linton | A service user has been employed to work on the website |
|  | Develop Obesity/ Learning Disability Strategy | PID, project plan and action plan in place | Marian Marsham and Stephan Brusch | December 2007 |
|  | Ensure local providers have policies and Standards regarding healthy eating, menu planning and physical activities | Caroline Walker Trust guidance have been distributed to all service providers. Contract Monitoring is starting to address healthy eating and well being (PIP and W.S) PIP has started breakfast club and has been awarded funding for healthy eating project. . Stephan drafted letter to contract monitoring officers. | Stephan Brusch and Ian Jones Janet Lang and John Higgins | April 2008 Post April 2008 |
|  | Seek opportunities for funding. | Supported Zodiac Art’s application for Lottery Grant (outcome by September 07) CPS money raised for 07/08 and for 08/09 Secured funding for Expert Patient Programme Summer of Sport Grants forwarded to organisations Stephan to write commission spec to include employment opportunity for people with ld and advertise to local organisations. | Stephan Brusch, Ian Jones | Ongoing CSP funding secured |
|  | Work with the Transport department | Invite a representative to a future meeting | Stephan Brusch, Prue Nielsen | Outstanding |
| Promote and support physical activities for people with learning disabilities in Westminster | Encourage walking as a form of physical activity | Use pedometers for service users. This is being piloted by PIP SW9. Roll out to CST Increase the number of people with learning disabilities attending walking groups by setting up walking group in spring 08. Continue to advertise existing walking groups Training arranged for Community Learning Disability Nurses, Physiotherapist in September . | Ruth Quigley Belinda Simpson Ruth Quigley and Stephan Brusch |  |
|  | Hold sports days with awards and certificates | Commissioning specification written and disseminated | SB |  |
|  | Develop additional physical activities | Provide extra structured activities such as climbing, canoeing, leisure pursuits that are outwards bounds Develop tennis and climbing session at Westways More supervised sessions at Leisure services and more opportunities such as trampling, swimming and bowling Need to write commissioning spec | Marian Sebaggala / Jonathan Hearn / Stephan Brusch |  |
| Promote healthy food for people with learning disabilities | Set up Individual and group training on cooking and healthy eating skills. | Completed pilot and this is being evaluated Good news story to be put into PCP newsletter | Alex Murley |  |
|  | Increase the number of people with learning disabilities eating five portion of fruit and vegetable | Advertised the food-coop in PCP bulletin. 2 volunteers will start working at the food coop. Ensure mainstream health promotion campaigns are accessible to people with learning disabilities | Head of Health Inequality and or Head of Health Promotion/ Stephan Brusch | Ongoing |
| Health promotion and education activities target people with learning disabilities (prevention and management) | Advice on providing healthy meals (menu planning) and healthy portions in Residential Houses | Caroline Walker Trust Guidelines have been distributed. See item on Contract monitoring | Ian Jones and Stephan Brusch | March 2008 |
|  | Advice on providing healthy meals (menu planning) and healthy portions in Day services | Caroline Walker Trust Guidelines have been distributed. See item on Contract monitoring | Ian Jones and Stephan Brusch, Pru Nielsen | See above |
|  | CPA and obesity | Provide health promotion advise (top tips to be active) on physical activities, nutrition and medication and side effect for care coordinator | Dr Ingrid Bohnen and Stephan Brusch | outstanding |
|  | Ensure that all people who are obese have a HAP | Audit obesity register once in place and cross-reference | Stephan Brusch and Marian Marsham |  |
|  | Link physical activities and services on nutrition advice to PCP | Our Choice and WES are leading on the development . Cast and crew appointed and filming has now finished. Waiting for post production. Liz to feedback at next meeting | Stephan Brusch | August 2008 |
|  | Ensure that people with diabetes have support around weight management | No actions so far | Sally Robinson/ Stephan Brusch |  |
| Public Health informs service delivery | Ensure that GP registers for learning disability and obesity are accurate and are audited six monthly. |  | Stephan Brusch and Mario Pasquali (?) | December 07 And March 2008 |
|  | Develop a WLDP Obesity Register | Once register is in place, send survey to find out what people’s needs are | Stephan Brusch, Andrew Greenhill and Derry Pitcaithly(?) | December 07 |
|  | Ensure that all people are weight (at least annually) | Purchased two weighing scales (Health at the Stowe and Lisson Grove Health Centre) |  | Completed |
| Primary Care and Learning Disability Staff deliver obesity prevention. | Issues of being overweight to be raised in routine GP appointments and at the annual health check |  | Ian Jones (?)/ Stephan Brusch |  |
|  | Ensure that NICE guidance apply to WLDP staff | look at best practice models | Marian Marsham |  |
|  | Ensure that carers and support worker have access to training on healthy eating and physical activities | Westminster PCT’s Health Trainer model was presented and signed off as a good model. Stephan to write commissioning specification | Nuria Madrono and Stephan Brusch | August 2008 |
|  | Train mainstream staff in learning disability awareness | Training session to the Dietetics team on learning disability awareness has been completed. Training to 23 GP practices undertaken. 3 Health Trainer sessions are being undertaken from January to March 08. | Stephan Brusch |  |