PROJECT DOCUMENTATION

Project Initiation document (pid)

Choosing the Chance to Change-

Reducing Obesity in people with learning disabilities

Release: Version 1

Date: 3rd September 2007

Authors: Stephan Brusch, Service Development Manager – Primary Care/ Learning Disabilities and Marian Marsham, Practice Development Nurse

Owner: Adrian Brown Public Health Consultant and Lead on Obesity, WPCT

Client: Westminster Primary Care Trust, Westminster City Council

Document Number:  1

# PID Document History

## Document Location

This document is only valid on the day it was printed.

The source of the document will be found on my network place/ Westminster Shared network/ Westminster Learning Disability Partnership/Obesity

## Revision History

Date of last revision: 3rd September 2007 , 6th September 2007

Date of this revision:  6th September

Final

## Approvals

This document requires the following approvals.

Signed approval forms are filed in the Management section of the project files.

| Name | Signature | Title | Date of Issue | Version |
| --- | --- | --- | --- | --- |
| Adrian Brown Mary Russell John Higgins |  | Public Health Consultant Health Improvement Team Leader Joint Commissioning Manager |  |  |

## Distribution

This document has been distributed to

| Name | Title | Date of Issue | Version |
| --- | --- | --- | --- |
| Janet Lang Brian Colman Helen Banham Cath Atlee Christopher Nicholas Meredith Gamble Dr Ingrid Bohnen Pru Nielsen Helen Banham Mary Russell Ruth Quigley Ian Jones Gabby Machell Lorna Hayes Dan Kisumbi Sally Robinson Richard Barker Jonathan Hearn Lindy Shufflebottom Ann Weeks Vivian Freeman | Service Manager Equality and Diversity Manager Service Manager – Residential, Day and Employment Services Assistant Director of Care Groups Community Health Development Coordinator Therapy Service Manager Consultant Psychiatrist Day Service Manager Manager Team Leader, Health Improvement Team Exercise Coordinator Nutrition & Dietetic Service Manager Chief Executive Westminster Society Carers Network PIP – Head of Services Diabetes Specialist Nurse Westminster Diabetes Centre Principal Sports & Leisure Services Manager Environment & Leisure Sports Development Manager - Delivery Westminster Sports Unit Moberly Sports & Education Centre Yarrow Housing Service Development Manager Children and Disability Team |  |  |

PROJECT BACKGROUND

General

Reducing overweight and obesity is a national and global priority (NICE 2006, WHO 2004) as the health risks associated with it are largely preventable, and prevalence is increasing.

This has particular implications for people with learning disabilities given the higher prevalence and co morbidity rates (Emerson 2005, Moore et al 2004, Rimmer and Yamaki 2006, Turner and Moss 1996, Yamaki 2005) and widely acknowledged unacceptable health inequalities experienced (Mencap 2007, DRC 2007, NPSA 2006).   Less than 10% of adults with learning disabilities eat a balanced diet (Robertson et al 2000) and over 80% of adults with learning disabilities ingage in levels of physical activities below the minimum recommendation (Messent et al 1998).

NICE guidance (2006) suggests that interventions should be tailored to meet the needs of different groups, and the approach used should be adjusted as needed.

Local

An audit of primary care Quality and Outcome Framework (QOF) registers of people with learning disabilities undertaken in June 2007 echoed the national findings of higher prevalence in obesity and other related co-morbidities such as diabetes.  BMI reading taken of 177 people with learning disabilities in Westminster (total local population is 400) established that 65% were either obese or overweight.  The prevalence rate for people with learning disabilities who had Diabetes was calculated at 9%.

The learning disability agenda is now reflected in the Obesity Strategy Group, Health Promotion Strategy Working Group and Physical Activity Sub-Group.

There are a number of local initiatives happening such as health groups and physical activities specifically targeting people with learning disabilities.  However there is no forum presently to oversee and coordinate these activities and to ensure that the target set in the Westminster Obesity Prevention and Treatment Strategy 2006-2009 are being met:

PROJECT DEFINITION

Project objectives

The overarching aim of this project is to reduce the level of obesity in people with learning disabilities by 2% in year 2007/08 measured by the QOF registers.  This target was set by the public health department as part of the development of Westminster Obesity Prevention and Treatment Strategy 2006-2009)

A number of objectives, with more detailed sub-goals, have been set to achieve this aim.  These objectives stem from an Involving People and stakeholder event hosted on the 27th June 2007 and are linked to the NICE guidance on managing obesity applied to people with learning disabilities.

- Promote and support physical activities for people with learning disabilities in Westminster.

- Promote healthy food for people with learning disabilities

- Health promotion and education activities target people with learning disabilities (prevention and management)

- Primary Care and Learning Disability Staff deliver obesity prevention.

- Public Health informs service delivery

- Partnership working.

Project scope

This is a two year project after which the aims and objectives will be reviewed.  Presently the QOF registers that are in place cover 30 GP practice in Westminster and approximately 2/3rd for the learning disability population.

Project deliverables

- An inter-sectoral working group with links to Health Promotion Steering Group and Obesity Strategy Group

- Annual Public Health Report based on the QOF registers and progress made against target.

- Accessible health information for people with learning disabilities on healthy eating

- Accessible health information on physical activities

- Individual sessions on weight management

- Group session on weight management

- Training for staff on weight management and obesity

- Referral pathway for people with learning disabilities who are obese

- Organisational standards and guidelines

- People with learning disabilities who are obese have a health action plan that outlines measurable actions to address their weight management

- Physical activity opportunities that are accessible to people with learning disabilities

Desired Outcomes

- An increase in people with learning disabilities who undertake the daily recommended physical activities.

- An increase in people with learning disabilities who eat the recommended 5 portion of fruit and vegetables a day.

- There is joint-up working between different stakeholders who work with people with learning disabilities.

Constraints

There are no new resources that can be dedicated to this project; instead it would need to be delivered as part of redesigning current service provision.  Any resources such as accessible health information would need to be developed in-house  There may be some difficulties in gather public health information on service users registered with a GP practice that does not provide the Local Enhanced Scheme for people with learning disabilities.

Interface

The project interfaces with a number of different organisations and stakeholders:

- Westminster City Council : Leisure and Culture, Transport and Streets, Contracting

- Westminster PCT: Dietetics, Public Health, PHIRO, Service Development

- Westminster Learning Disability Partnership (Community Team, Day Services, Service Development)

- Local Voluntary Organisations providing services to people with learning disabilities (Westminster Society, St Pancras Housing, Life Opportunity Trust, Yarrow Housing, Outlook, PIP, The Advocacy Project,)

- Children and Disability Team

- Carers Network

- Family Advisory Service

- Children Services

- Our Choice

- People with learning disability

- Carers and parents of people with learning disabilities

- Health Facilitators

PROJECT APPROACH

A local consultation event that used café style consultation with local stakeholders highlighted the kind of activities that people liked to see happen locally and these have were fed into the project plan.  Given the constraint of the project, outlined above all activities and resources would need to be completed in-house.

PROJECT TOLERANCES AND CONTROLS

To oversee the project plan a working group will be established which will consist of the main stakeholders.  This group will meet on a regular basis to ensure that the actions are being implemented and the plan updated.

On a regular basis progress reports and or presentation will be made to the Obesity Strategy Group, Health Promotion Strategy Working Group, Quarterly Performance / Clinical Governance Meeting, Physical Activity Sub Group and Partnership Board.  Any outcome and required actions from these progress reports will be fed back to the working group.

The Service Development Manager or the Professional Development Nurse will inform the relevant leads if it is anticipated that the target will not be met.

BUSINESS CASE

This project is in support of the implementation of the following national drivers:

- ‘Guidance on the prevention, identification, assessment and management obesity in Adults and Children (NICE 2006)

- Valuing People (Person Centred Planning and Health Action Planning) (DoH 2001)

- ‘Closing the Gap’ (DRC 2006) and ‘Promoting Equality (DoH 2007)

- ‘The Better Metrics’ (DoH 2004).

And local drivers:

- Westminster PCT’s Corporate Objective 2007-08, Principal Corporate Objective 2.6.6: 50% of people known to the service to have a health action plan

- Obesity Strategy Strategic Priorities Performance Management Framework 3.8: Reduce level of obesity in target group by 2%

- The Big Plan 2005-08: Improve Access to NHS services including GPs and hospitals.

- Westminster Learning Disabilities Clinical Governance objective: To reduce overweight/obesity rates amongst in borough WLDP service users (Health Care Commission standard: 7th Domain C22 – improve health and narrow health inequality, C23 – systematic health promotion programmes meeting national frameworks.)

- Westminster PCT’s and City Council’s Disability Equality Scheme

Options

- Do Nothing

This option would lead to further health inequalities experienced by this client as it would be likely that the prevalence of obesity and diabetes would increase.  This would lead to financial implication for the PCT and City Council relating to the management of these conditions.  Without this coordinated project approach, the Obesity Strategy Group is unlikely to meet its target in reducing the prevalence of obesity in people with learning disability by 2% in 07/08 and 08/09.   Presently there is no forum where this work-stream could be taken forward.

- Project plan is rolled out as described

This would lead to a coordinated approach to manage obesity with clear milestones, measurable outcomes and reporting structure.

PROJECT ORGANISATION STRUCTURE

Aim:

A working group to oversee the implementation of the project: Choosing the Chance to Change- Reducing Obesity in people with learning disabilities

Objectives:

- To provide a forum for sharing information and ideas regarding local and best practice in obesity prevention and management

- To oversee and monitor the implementation of the Project Plan.

- To progress specific tasks within the Project  Plan

- To provide updates and reports regarding mental health promotion to the LIT, Health Promotion Strategy Group and Working Group, when necessary

- To champion this project within the relevant organisation

- To assist in planning health promotion campaigns, in conjunction with HIMP, PHIRU etc.

Suggested Membership:

- Service user

- Representative from Public Health

- Representation from Health Improvement Team (HIMP)

- Representation from Dietetics

- Person Centred Planning Officer – Claudia Linton

- Community Health Development Worker

- Carers Representative – Lorna Hayes

- Service Development Manager for Learning Disability – Stephan Brusch

- Physiotherapist from WLDP

- Andrew Greenhill (The Croxley Project)

- Pru Nielsen -Day Service Manager

- Marian Marsham (Professional Development Nurse)

- Alex Murley (Occupational Therapist)

- Psychologist

- Representation from Dietetics

- Speech and Language Therapy

To invite as appropriate

- Mario Pasquali Manager of IM&T team/ Derry Pitcaithly, System and Project Officer

- Dr Ingrid Bohnen and Dr Rahim Clinical Psychiatrists

- Representative from Leisure Services

- Representative from Physical Disability Services

- Primary Care representative – GP/Practice Nurse

- Environmental Health representative

- Contract Monitoring/ John Higgins and Janet Lang

- Nuria Madrono- Training and Development Manager

- PIP- Travel training

### Frequency of Meetings

It is proposed that the sub-group meet every 8 weeks

COMMUNICATION PLAN

Feedback from the Stakeholder event highlighted how much importance local stakeholders and service users placed on ongoing communication.  The expressed need was to have clear communication channels that provide updates and information as well as provide motivation to staff and to service users.

Project Initiation Document formally presented:

- Invite all local stakeholders who attended the event on the 27th June for feedback.

Project Initiation Document send via email send to contacts on the distribution list.

Outcomes and Project Plan send via PCP bulletin, Monthly Forum, email to:

Health Facilitator

Carers Network

Family Advisory Service

Children Services

Westminster Learning Disability Partnership

Service Development

The Advocacy Project

Westminster Society

St Pancras Housing

Life Opportunity Trust

Yarrow Housing

Outlook

PIP

The Advocacy Project

GP services

Regular updated project plan on an annual basis or through a formal presentation:

- Obesity Strategy Group

- Health Promotion Strategy Group

- Physical Activity Sub-group

- Partnership Board

- Senior Manager and Clinician Quarterly performance management meeting

- Westminster PCT’s Disability Equality Scheme Implementation meeting

Regular updated project plan on a two monthly basis:

John Higgins

Janet Lang

Marian Marsham

Brian Colman

Lorna Hayes

Helen Banham

Lynn Coventry (PHIRO)

Westminster Society

St Pancras Housing

Life Opportunity Trust

Yarrow Housing

Outlook

PIP

The Advocacy Project

Carers Network

Family Advisory Service

Children Services

The Advocacy Project

Westminster Society

St Pancras Housing

Life Opportunity Trust

Yarrow Housing

Outlook

PIP

Accessible flyer and Partnership Newsletter, presentation, website and person centred planning tool such as a CD-rom (outlining local resources and good news stories):

Service users, Person Centred Planning and Health Facilitators

PROJECT QUALITY PLAN

Customer quality expectations

Any project deliverables need to be acceptable to people with learning disabilities in Westminster and the members of the Partnership Board.  They need to conform to Westminster PCT or Westminster City Council’s quality standards, such as for training or for developing health promotion material.

Views and sign up for this project needs to be sought from all local stakeholders.

| Project Plan Choosing the Chance to Change- Reducing Obesity in people with learning disabilities (September 07– September 09) |
| --- |
| Project objectives | Item | Action | Lead | Date |
| Partnership working | Set up working group and set up monitoring structure | Set up working group Present to the Obesity Strategy Group Link to wider Equality Agenda | Stephan Brusch and Marian Marsham Brian Colman | Date for first meeting set by SeptemberSeptember 2007 |
|  | Link to the Olympics/ Para-Olympics 2012 |  | Alan Whetherley Stephan Brusch |  |
|  | Implement Obesity Communication strategy | Hold feedback event Develop a champion in each service to take obesity management forward | Marian Marsham and Stephan Brusch | Stakeholder event to be held by End of November 07 |
|  |  | WLDP’s website includes information on physical activities and other health information | Working group Derry Pitcaithly |  |
|  | Develop Obesity/ Learning Disability Strategy |  | Marian Marsham and Stephan Brusch |  |
|  | Ensure local providers have policies and Standards regarding healthy eating, menu planning and physical activities | Link with Caroline Walker Trust and disseminate Check in Contract Monitoring that training and policies are in place | Stephan Brusch Janet Lang and John Higgins | January 2008 |
|  | Develop a pcp resource on physical activities, good places to eat | Health Map including physical activities and places to eat | Claudia Linton |  |
|  | Ensure that there are clauses of inclusion in Service Level Agreements (influence commissioning) |  | Brian Colman? Stephan Brusch |  |
|  | Seek opportunities for funding | Supported Zodiac Art’s application for Lottery Grant (outcome by September 07) | Stephan Brusch, Andrew Greenhill and John Higgins |  |
|  | Work with the Transport department | Active transport such as walking bus to day centre. Link to Travel training at PIP |  |  |
| Promote and support physical activities for people with learning disabilities in Westminster | Encourage walking as a form of physical activity | Use pedometers for service users. This is being piloted by PIP SW9. Increase the number of people with learning disabilities attending walking groups | Ruth Quigley Belinda Simpson Ruth Quigley and Stephan Brusch |  |
|  | Hold sports days with awards and certificates |  |  |  |
|  | Develop additional physical activities | Provide extra structured activities such as climbing, canoeing, leisure pursuits that are outwards bounds Develop tennis and climbing session at Westways More supervised sessions at Leisure services and more opportunities such as trampling, swimming and bowling | Marian Sebaggala + Andrew Shelley |  |
| Promote healthy food for people with learning disabilities | Set up Individual and group training on cooking and healthy eating skills. | Set up weight management group | Alex Murley? |  |
|  | Increase the number of people with learning disabilities eating five portion of fruit and vegetable | Advertise the food-coop Ensure mainstream health promotion campaigns are accessible to people with learning disabilities | Community Health Development Manager/ Stephan Brusch |  |
| Health promotion and education activities target people with learning disabilities (prevention and management) | Advice on providing healthy meals (menu planning) and healthy portions in Residential Houses |  | Ian Jones and Stephan Brusch |  |
|  | Advice on providing healthy meals (menu planning) and healthy portions in Day services |  | Ian Jones and Stephan Brusch, Pru Nielsen |  |
|  | CPA and obesity | Provide health promotion advise (top tips to be active) on physical activities, nutrition and medication and side effect for care coordinator | Dr Ingrid Bohnen and Stephan Brusch |  |
|  | Ensure that all people who are obese have a HAP |  | Stephan Brusch and Marian Marsham |  |
|  | Link physical activities and services on nutrition advice to PCP | Develop a video and CD rom of physical activities etc. |  |  |
|  | Ensure that people with diabetes have support around weight management |  | Sally Robinson/ Stephan Brusch |  |
| Public Health informs service delivery | Ensure that GP registers for learning disability and obesity are accurate and are audited six monthly. |  | Stephan Brusch and Mario Pasquali (?) | December 07 |
|  | Develop a WLDP Obesity Register | Once register is in place, send survey to find out what people’s needs are | Stephan Brusch, Andrew Greenhill and Derry Pitcaithly(?) | December 07 |
|  | Ensure that all people are weight (at least annually) | Seek access to scales for non-ambulant people |  |  |
| Primary Care and Learning Disability Staff deliver obesity prevention. | Issues of being overweight to be raised in routine GP appointments and at the annual health check |  | Ian Jones (?)/ Stephan Brusch |  |
|  | Ensure that NICE guidance apply to WLDP staff | look at best practice models | Marian Marsham |  |
|  | Ensure that carers and support worker have access to training on healthy eating and physical activities |  | Nuria Madrono |  |
|  | Train mainstream staff in learning disability awareness | Training session to the Dietetics team on learning disability awareness has been completed | Stephan Brusch |  |

| INITIAL RISK LOG |
| --- |
| Risk Identifier: |  | Author: | Stephan Brusch | Date Identified: |  |
| Description: |  |
| Risk Category: |  | Likelihood : |  | Risk consequence score: |  |
| Countermeasure: |  |
| Owner: |  | last update |  | Status: |  |
| Risk Identifier: |  | Author: | Stephan Brusch | Date Identified: |  |
| Description: |  |
| Risk Category: |  | Likelihood : |  | Risk consequence score: |  |
| Countermeasure: |  |
| Owner: |  | last update |  | Status: |  |
| Risk Identifier: |  | Author: | Stephan Brusch | Date Identified: |  |
| Description: |  |
| Risk Category: |  | Likelihood : |  | Risk consequence score: |  |
| Countermeasure: |  |
| Owner: |  | last update |  | Status: |  |
| Risk Identifier: |  | Author: |  | Date Identified: |  |
| Description: |  |
| Risk Category: |  | Likelihood : |  | Probability: |  |
| Countermeasure: |  |
| Owner: |  | last update |  | Status: |  |
| Risk Identifier: |  | Author: |  | Date Identified: |  |
| Description: |  |
| Risk Category: |  | Likelihood : |  | Probability: |  |
| Countermeasure: |  |
| Owner: |  | last update |  | Status: |  |