Outcomes for the role of Regional Programme Manager: PSA 16 Employment (mental health and learning disabilities, with scope for extension into the offender programme

Agenda for Change Band 8b

This document sets out the expected outcomes to be achieved by the role holder focussing on the delivery of DH’s PSA 16 Employment strategy for mental health and learning disabilities (supported by regional allocation of £340,000 for PSA 16 mental health and learning disabilities) up to March 2010..

The plan will be extended for 2010/11 and In addition to this, the intention is to support employment for offenders. However, this programme will not be developed until later in the year.

Associated documents: Induction programme, Appraisal, Personal Development Plans and the generic job description and person specification.

Time period: [12 months]

Generic Deliverables

| OUTCOME | DELIVERY MECHANISM | TARGET MILESTONES |
| --- | --- | --- |
| Ensure focus on delivery at local level, working effectively within existing virtual teams, but maintaining focus on local local delivery of increased employment for PSA 16 target groups: with DH’s Regional Valuing People team- with the SHA’s mental health improvement team with the Regional Offender Health team with the GO team and their partners The initial priority will be working with learning disabilities and mental health services | Housing and Employment specialist roles to be part of ‘virtual team’ & PSA 16 Delivery group, working closely with: GO lead & housing and employment agencies CLG Regional Resource Team NHS and adult social care arrangements (Darzi programme, Joint Improvement Partnership) Existing partnership arrangements for LD and MH | DH Social care team will work with PSA 16 delivery group & networks, NHS and adult social care regional arrangements |
| People with learning disabilities & carers engaged in shaping plans via existing Learning Disability Partnership Board structures Co-ordination of action between the Regional Learning Disabilities Programme Board and Local Partnership Boards, linking with the Joint Improvement Partnership and RIEP | Use existing engagement structures: Engagement in the Learning Disabilities delivery plan for Valuing People is through Local Partnership Boards and the Regional Learning Disabilities Programme Board. The Regional Forum for People with Learning Disabilities and the Regional Valuing Families Forum will be engaged Regional Partnership Board lead officers and JIP overview group | Regional plan agreed in consultation with Partnership Boards |
| People with mental ill-health & carers shape plans | Use existing engagement structures MH Local Implementation Teams (LITs) LIT engagement programmes in locality areas with PCTs, Trusts, LAs & providers Regional MH Commissioners Group | Regional priorities developed in collaboration with MH LITs/ MH Commissioning Group |
| Improved understanding of performance & progress | Improve information on baseline of employment for people with learning disabilities and severe mental illnessvia social are and NHS data sets (offender group data set to be developed at a later stage | Improvement in social care and NHS data to assess progress |
| Assessment of effectiveness of supported employment schemes completed to inform future commissioning | Consult with ADASS to confirm regional priority and if supported tender for capacity to undertake review, drawing on a national specification to be developed | Firm view to be included in Regional Delivery Plan |
| Increased support and sign up to provision of supported employment, with public sector providing leadership in this area | Support and facilitate specific events & initiatives with public sector employers, (LA & NHS in particular) ‘Valued in public ‘ events Sign up to Local Employment Projects; Provide apprenticeships to PSA 16 groups LAs to use Future Jobs Fund to provide opportunities / work placements. Share good practice established via RET in recruiting and retaining people from target groups. | To be included in Regional Delivery Plan |

Learning Disabilities Deliverables

| OUTCOME | DELIVERY MECHANISM | TARGET MILESTONES |
| --- | --- | --- |
| Overall regional target for numbers of people with LD in employment will be agreed | Regional LD Programme Board will ask Partnership Boards to agree a target and this will be confirmed in the Regional Annual Plan or November 2009, if this is achievable | tbc |
| PSA 16 plan will build on existing regional JIP project set up to Understand current regional position Share learning Increase numbers of people in employment. | Collate baseline data on numbers in employment Publish best practice guidance & models Support all 9 LAs to develop/improve & deliver LD employment strategies Share learning from Leicester Project Search Share good practice arising from RET in recruiting and retaining people with LD. | Baseline data collected Information published Strategies in place with target numbers Good practice shared |
| Jobs secured for young people in the transition age group 14-25. Ensuring that even those with most complex needs are supported. | Regional programme for ‘Getting a Life’ will be developed, with support from national team and making links to existing JIP Person Centred Planning project | Regional Programme funded to share learning. ‘Getting A Life’ aims for employment for 75% of people worked with. |
| Develop best practice for adults beyond transition | Support a further local employment project for adults, using evidence based approaches | Project tbc in Regional Delivery Plan November 2009 |
| Family carers are engaged in the programme and support the changes | ‘Families supporting employment’ road shows and links made to broader Regional Carers Strategy | Family road shows will be delivered by March 2010 |

Mental Health Deliverables

| OUTCOME | DELIVERY MECHANISM | TARGET MILESTONES |
| --- | --- | --- |
| Assess and understand LIT ambition for target numbers of people with MH needs in the PSA 16 group (those with severe mental illness) | SHA improvement team, via links with MH Local Implementation Teams will assess ambition and develop overall regional target | Target date to confirm in regional delivery plan by November 2009p |
| At least one site in East Midlands will choose this as a priority in their MH commissioning plans (note that no LA s include this PSA 16 as a priority in their LAA) | Use PSA 16 funding/ match funding where available and seek demonstration site for best practice in the region. The criteria for this could include: building on the existing JIP MH and personalisation projects in each locality use of personal budgets to promote flexible support to help improve access build in links to IATP employment team to provide coordinated approach | Aim for for best practice site to be identified in Regional Delivery Plan, November 2009 |